## Sheet1
Andrew Taormino, Retail Forum | Cosc 412
|  |  |  | February | [12 empty] | March | [30 empty] | April | [29 empty] | May
Task | Percent Complete | Date Started | Date Completed | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  |  |  | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
Brainstorm
Brainstorm Forum Implementation | 100% | 2020-02-17 | 2020-02-29 | bar: February 17 Mo to February 29 Sa
Brainstorm Adding/Removing Items | 100% | 2020-02-17 | 2020-02-27 | bar: February 17 Mo to February 27 Th
Think of Structure of Website | 100% | 2020-02-17 | 2020-02-25 | bar: February 17 Mo to February 25 Tu
Think of Website Name | 100% | 2020-02-17 | 2020-02-20 | bar: February 17 Mo to February 20 Th
Milestone: Finish Brainstorming
Gathering Resources
Get Domain Name | 100% | 2020-03-01 | 2020-03-02 | bar: March 1 Su to March 2 Mo
Get Hosting on Azure | 100% | 2020-03-02 | 2020-03-15 | bar: March 2 Mo to March 15 Su
Research into Azure | 100% | 2020-03-02 | 2020-03-20 | bar: March 2 Mo to March 20 Fr
Research Wordpress/plugins | 100% | 2020-03-07 | 2020-03-30 | bar: March 7 Sa to March 30 Mo
Milestone:Finish Resource Gathering
Planning
Acquire Requirements | 100% | 2020-02-20 | 2020-02-23 | bar: February 20 Th to February 23 Su
Create Repo on GitHub | 100% | 2020-03-01 | 2020-03-02 | bar: March 1 Su to March 2 Mo
Create SPMP | 100% | 2020-02-25 | 2020-03-10 | bar: February 25 Tu to March 10 Tu
Design Review Meeting | 0% | TBD
Tool Review Meeting | 0% | TBD
Create Use Cases | 100% | 2020-03-10 | 2020-03-15 | bar: March 10 Tu to March 15 Su
Design Milestone Review | 100% | 2020-04-15 | 2020-04-20 | bar: April 15 We to April 20 Mo
Create System Test Plan | 100% | 2020-04-21 | 2020-04-27 | bar: April 21 Tu to April 26 Su
Create Final Presentation | 0% | 2020-05-01 | 2020-05-04 | bar: April 30 Th to May 3 Su
Milestone: Finish Planning
Design Website
Create Homepage | 100% | 2020-04-01 | 2020-04-05 | bar: April 1 We to April 5 Su
Create Login/Registration Page | 100% | 2020-04-10 | 2020-04-13 | bar: April 6 Mo to April 13 Mo
Create Separate Logins for Different Users | 100% | 2020-04-20 | 2020-04-23 | bar: April 20 Mo to April 23 Th
Add Ability to Add/Remove Items | 80% | 2020-04-05 | 2020-04-25 | bar: April 5 Su to April 25 Sa
Create Purchase Page | 100% | 2020-04-14 | 2020-04-16 | bar: April 14 Tu to April 16 Th
Create Navbar | 100% | 2020-04-15 | 2020-04-16 | bar: April 15 We to April 20 Mo
Create Search Bar | 50% | 2020-04-15 | 2020-04-20 | bar: April 20 Mo to April 21 Tu
Create Buttons to Other Pages | 100% | 2020-04-20 | 2020-04-21
Milestone:Finish Website