## Sheet1
Milestone | Completion of Milestone(With Explanation if Necessary)
Brainstorm Forum Implementation | Forum brainstorming and implementation is complete.
Brainstorm Adding/Removing Items | Ideas have been used to develop the ability to add and remove items from the website.
Designed Website Name and Structure | Website name is RetailForums and is structured similarly to that of Amazon or Ebay.
Hosting Website and used domain name | The website is hosted on Microsoft Azure and has a domain name.
Research into Azure and Wordpress | Research has been completed to use Azure and to use specific plugins for Wordpress, specifically to be able to purchase items, have specific user logins, and the ability to creat forums.
Created Repo | Repository is up on GitHub. https://github.com/ataorm1/412IndividualProject
Finished SPMP and according Diagrams | SPMP along with the WBS, Ganntt Chart and the Use Case Diagrams are complete and up on GitHub.
Met for Design Review/Tool Selection | Unfortunately, due to me losing track of time and my own negligence,I had missed the opportunity to have the meeting with the professor for the Design Review and the Tool Selection.
Created System Test Plan | System test plan is complete and up on the GitHub.
Created Final Presentation | Final Presentation is not complete, however it will be so within a matter of days, by the specific time layed out in the Ganntt chart. I want to tweak and finish some issues that I have with the website before I completely finish the presentation.
Finished Developing Website | Website is mostly complete. The basic functionality, like the forums, home page, purchase webpage, and user login/registration are complete. However I am having some issues with the ability to remove items and the search bar is having some issues.
Created a homepage | Home page is complete.
Created User Login/Registration | User login and registration is complete.
Developed different logins/pages for different users | Customers, Retailers, and administrators have separate login pages and will see different webpages on the website.
Ability to add/remove items being sold | I have been able to add items to the website, however the ability to remove items has been a little more difficult when it comes to Wordpress's database. I will have this issue fixed very shortly.
Have forums built into each item | When an item is created, a new forum is created along with it to ensure the smoothest ability to communicate with customers.
Have a purchase webpage | The ability to purchase items with a redirect webpage has been added to the website.
Developed Navbar/Search bar /buttons to webpages | Navbar and buttons to separate webpages have been added, however I am having some issue to get the search bar working since it runs off of key words. This issue will also be resolved very shortly.